## Agentic Integration
PHASE | Task | Description | Priority | Status | Progress % | Deliverable | Start Date | Completed Date | Blockers | GitHub/PR | Notes
PHASE 3.1 | Task 1: Master StateGraph Setup
PHASE 3.1 | Subtask 1.1: Master Agent State Definition | Define the unified state class holding user messages, session ID, CUC, DIC, and execution plan. | High | Complete | 100 |  | 2026-07-28 | 2026-07-29 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Foundation for LangGraph orchestration.
PHASE 3.1 | Subtask 1.2: Graph Nodes & Edge Topology | Wire state graph edges connecting Parser, Clarification, Planner, Scout, Platform, and Memory nodes. | High | Complete | 100 |  | 2026-07-28 | 2026-07-29 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Built using LangGraph StateGraph.
PHASE 3.1 | Task 2: Conversation Parser & Intent NLU |  |  |  | 100 | DAG execution engine service
PHASE 3.1 | Subtask 2.1: Qwen 32B Intent Extractor | Connect OpenRouter Qwen 32B model to parse natural language user intent into CUC contract. | High | Complete | 80 | Run-state persistence layer | 2026-07-29 | 2026-07-29 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Handles messy user phrasing.
PHASE 3.1 | Subtask 2.2: CUC Confidence Gate | Implement exact required-field confidence scorer with threshold gate (0.85). | High | Complete | 100 | Validation API endpoint | 2026-07-06 | 2026-07-08 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Fixed confidence estimator loop bug.
PHASE 3.1 | Task 3: Planning Engine & Feasibility
PHASE 3.1 | Subtask 3.1: Intent-to-Plan Mapper | Map parsed CUC intent to a 7-step execution plan sequence for downstream agents. | High | Complete | 100 | Cleaning + validation nodes | 2026-07-29 | 2026-07-07 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Deterministic plan generation.
PHASE 3.1 | Subtask 3.2: Plan Feasibility Validator | Check plan steps against system requirements before triggering execution. | Critical | Complete | 100 | Split + export nodes (SCOPE to SPLIT) | 2026-07-06 | 2026-07-30 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Rejects impossible plans.
PHASE 3.1 | Task 4: Ingestion Compiler Engine | [8 empty] | https://github.com/AJ6002/aiconnex_demo/tree/30jul
PHASE 3.1 | Subtask 4.1: Plugin Discovery & Registry | Auto-discover and register 22 ingestion plugins across 5 pipeline stages. | High | Complete | 100 | E2E test report | 2026-07-29 | 2026-07-30 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Fail-closed on ambiguous file types.
PHASE 3.1 | Subtask 4.2: Multi-Format Harvester | Extract, parse, and assemble CSV, ZIP, XLSX, TSV, and Parquet data into a combined table. | High | Complete | 100 |  | 2026-07-29 | 2026-07-30 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Handles single files and ZIP archives.
PHASE 3.1 | Task 5: Scout Agent & Profiling
PHASE 3.1 | Subtask 5.1: Dataset Intelligence Profiler | Profile dataset dimensions, missing ratios, quality alerts, and candidate target columns. | High | In Progress | 70 |  | 2026-07-30 | 2026-07-30 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Real file inspection (no fake data).
PHASE 3.1 | Subtask 5.2: DIC Completeness Validator | Validate DIC schema completeness after compilation and surface quality warnings | Medium | In Progress | 70 |  | 2026-07-30 | 2026-07-30 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Prevents downstream null crashes.
PHASE 3.1 | Task 6: LLM-Driven HITL Flow
PHASE 3.1 | Subtask 6.1: ETP Question Generator | Inject HTDS specification into Qwen 32B to generate non-technical plant manager questions. | High | Complete | 100 |  | 2026-07-30 | 2026-07-31 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Tailored for ETP Plant Managers.
PHASE 3.1 | Subtask 6.2: Terminal Pause & Resume | Halt terminal execution cleanly on input() for each user turn during HITL session. | High | Complete | 100 |  | 2026-07-30 | 2026-07-31 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Zero auto-skipping loops.
PHASE 3.1 | Task 7: Recipe Resolution & DAG Pool
PHASE 3.1 | Subtask 7.1: Multi-DAG Recipe Resolver | Query 1,993-entry DAG mapping JSON to select 3-5 distinct candidate algorithms. | High | Complete | 100 |  | 2026-07-30 | 2026-07-31 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Guarantees algorithm diversity.
PHASE 3.1 | Subtask 7.2: Candidate Recipe Generation | Build structured CandidateRecipe objects containing hyperparameters and feature configs. | Medium | Complete | 100 |  | 2026-07-30 | 2026-07-31 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Machine-readable recipe format.
PHASE 3.1 | Task 8: Platform ML Engine & Ensemble
PHASE 3.1 | Subtask 8.1: ThreadPool Parallel Trainer | Execute parallel candidate training across background threads using ThreadPoolExecutor. | High | Complete | 100 |  | 2026-07-31 | 2026-07-31 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Max 3 parallel worker threads.
PHASE 3.1 | Subtask 8.2: Stacked Ensemble Meta-Learner | Train meta-learner combining out-of-fold predictions from base candidate models. | High | Complete | 100 |  | 2026-07-31 | 2026-07-31 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Uses real regression trainer.
PHASE 3.1 | Task 9: MCDA Evaluation Triad
PHASE 3.1 | Subtask 9.1: Scorer Agent Evaluation | Calculate hard quantitative metrics (R², MAE, RMSE, MAPE, Latency, Size). | High | Complete | 100 |  | 2026-07-31 | 2026-07-31 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | 50% weight in MCDA score.
PHASE 3.1 | Subtask 9.2: LLM Judge Agent Evaluation | Evaluate model compliance against physical domain constraints using LLM rubric. | High | Complete | 100 |  | 2026-07-31 | 2026-07-31 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | 30% weight in MCDA score.
PHASE 3.1 | Subtask 9.3: Selector Agent Winner Pick | Compute final MCDA scores (50% Scorer + 30% Judge + 20% Intent) and select winner. | High | Complete | 100 |  | 2026-07-31 | 2026-07-31 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Fair multi-criteria decision.
PHASE 3.1 | Task 10: Telemetry & MLflow
PHASE 3.1 | Subtask 10.1: Multi-Node Emitters | Emit telemetry events for Parser, Planner, Scout, HITL, and Platform nodes. | High | Complete | 100 |  | 2026-07-31 | 2026-07-31 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Covers all 5 pipeline phases.
PHASE 3.1 | Subtask 10.2: MLflow SQLite Store Setup | Store experiment runs, metrics, parameters, and artifacts in ./mlruns. | Medium | Complete | 100 |  | 2026-07-31 | 2026-07-31 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Complete experiment history.
PHASE 3.1 | Task 11: CLI Orchestrator & Manifests
PHASE 3.1 | Subtask 11.1: End-to-End Terminal Runner | Wire interactive terminal pipeline orchestrator running Phase 1 to Phase 5. | High | Complete | 100 |  | 2026-07-31 | 2026-07-31 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Fully tested in terminal.
PHASE 3.1 | Subtask 11.2: 3-Layer Manifest Builder | Package Conversation, Discovery, and Decision manifests into compilation_package.json. | High | Complete | 100 |  | 2026-07-31 | 2026-07-31 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Immutable handoff package.
PHASE 3.1 | Task 12: UI Branch Sync & Integration
PHASE 3.1 | Subtask 12.1: Merge 30jul into new-chat-UI | Merge all Phase 3 agentic backend commits from 30jul branch into new-chat-UI. | High | Not Started | 0 |  | 2026-08-03 |  | Waiting for branch switch | #new-chat-UI https://github.com/AJ6002/aiconnex_demo/tree/new-chat-UI | Current Next Step.
PHASE 3.1 | Subtask 12.2: Connect Flask API to React UI | Connect React frontend chat components to the live agentic backend API endpoints. | High | Not Started | 0 |  | 2026-08-03 |  | Depends on Subtask 12.1 | #new-chat-UI https://github.com/AJ6002/aiconnex_demo/tree/new-chat-UI | Final Phase 3 Milestone.
PHASE 3.1 | Subtask 12.3: Testing of the Terminal End to End |  |  |  | 20