## Phase 3 _Agentic Integration
PHASE | Task | Description | Priority | Status | Progress % | Deliverable | Start Date | Completed Date | Blockers | GitHub/PR | Notes
PHASE 3.1 | Task 1: Master StateGraph Setup
PHASE 3.1 | Subtask 1.1: Master Agent State Definition | Define the unified state class holding user messages, session ID, CUC, DIC, and execution plan. | High | Complete | 100 | aiconnex_agent/state.py | 2026-07-28 | 2026-07-29 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Foundation for LangGraph orchestration. Provides immutable contract storage across chat and execution loops.
PHASE 3.1 | Subtask 1.2: Graph Nodes & Edge Topology | Wire state graph edges connecting Parser, Clarification, Planner, Scout, Platform, and Memory nodes. | High | Complete | 100 | aiconnex_agent/graph.py | 2026-07-28 | 2026-07-29 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Built using LangGraph StateGraph. Ensures deterministic node routing and checkpointer state saving.
PHASE 3.1 | Task 2: Conversation Parser & Intent NLU
PHASE 3.1 | Subtask 2.1: Qwen 32B Intent Extractor | Connect OpenRouter Qwen 32B model to parse natural language user intent into CUC contract. | High | Complete | 100 | chatbot/backend/extraction.py | 2026-07-29 | 2026-07-29 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Handles messy user phrasing. Robustly maps ambiguous user prompts to canonical problem types.
PHASE 3.1 | Subtask 2.2: CUC Confidence Gate (85%) | Implement exact required-field confidence scorer with threshold gate (0.85). | High | Complete | 100 | aiconnex_agent/parser/confidence_scorer.py | 2026-07-29 | 2026-07-30 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Fixed confidence estimator loop bug. Routes low-confidence intents to HITL clarification node.
PHASE 3.1 | Task 3: Planning Engine & Feasibility
PHASE 3.1 | Subtask 3.1: Intent-to-Plan Mapper | Map parsed CUC intent to a 7-step execution plan sequence for downstream agents. | High | Complete | 100 | aiconnex_agent/planning/intent_plan_mapper.py | 2026-07-29 | 2026-07-30 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Deterministic plan generation. Produces structured step arrays targeting Scout and Platform agents.
PHASE 3.1 | Subtask 3.2: Plan Feasibility Validator | Check plan steps against system requirements before triggering execution. | Medium | Complete | 100 | aiconnex_agent/planning/planning_engine.py | 2026-07-29 | 2026-07-30 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Rejects impossible plans. Verifies feature requirements prior to expensive platform model runs.
PHASE 3.2 | Task 4: Ingestion Compiler Engine
PHASE 3.2 | Subtask 4.1: Plugin Discovery & Registry | Auto-discover and register 22 ingestion plugins across 5 pipeline stages. | High | Complete | 100 | aiconnex_zip_compiler/plugins/registry.py | 2026-07-29 | 2026-07-30 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Fail-closed on ambiguous file types. Enables seamless auto-selection of file harvesters.
PHASE 3.2 | Subtask 4.2: Multi-Format Harvester | Extract, parse, and assemble CSV, ZIP, XLSX, TSV, and Parquet data into a combined table. | High | Complete | 100 | aiconnex_zip_compiler/compiler.py | 2026-07-29 | 2026-07-30 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Handles single files and ZIP archives. Generates standardized all_groups_combined.csv output.
PHASE 3.2 | Task 5: Scout Agent & Profiling
PHASE 3.2 | Subtask 5.1: Dataset Intelligence Profiler | Profile dataset dimensions, missing ratios, quality alerts, and candidate target columns. | High | Complete | 100 | aiconnex_agent/scout/scout_node.py | 2026-07-30 | 2026-07-30 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Real file inspection (no fake data). Populates DIC contract with exhaustive dataset stats.
PHASE 3.2 | Subtask 5.2: DIC Completeness Validator | Validate DIC schema completeness after compilation and surface quality warnings. | Medium | Complete | 100 | aiconnex_agent/scout/dic_validator.py | 2026-07-30 | 2026-07-30 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Prevents downstream null crashes. Ensures zero missing mandatory fields in the DIC payload.
PHASE 3.3 | Task 6: LLM-Driven HITL Flow
PHASE 3.3 | Subtask 6.1: ETP Question Generator | Inject HTDS specification into Qwen 32B to generate non-technical plant manager questions. | High | Complete | 100 | chatbot/backend/hitl_extraction.py | 2026-07-30 | 2026-07-31 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Tailored for ETP Plant Managers. Translates data science parameters into plain business choices.
PHASE 3.3 | Subtask 6.2: Terminal Pause & Resume | Halt terminal execution cleanly on input() for each user turn during HITL session. | High | Complete | 100 | chatbot/backend/hitl_flow.py | 2026-07-30 | 2026-07-31 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Zero auto-skipping loops. Synchronously holds StateGraph state while awaiting operator input.
PHASE 3.3 | Task 7: Recipe Resolution & DAG Pool
PHASE 3.3 | Subtask 7.1: Multi-DAG Recipe Resolver | Query 1,993-entry DAG mapping JSON to select 3-5 distinct candidate algorithms. | High | Complete | 100 | aiconnex_agent/platform/multi_dag_resolver.py | 2026-07-30 | 2026-07-31 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Guarantees algorithm diversity. Filters candidate recipes matching dataset profile family.
PHASE 3.3 | Subtask 7.2: Candidate Recipe Generation | Build structured CandidateRecipe objects containing hyperparameters and feature configs. | Medium | Complete | 100 | aiconnex_agent/schemas.py | 2026-07-30 | 2026-07-31 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Machine-readable recipe format. Prepares candidate specs for parallel execution.
PHASE 3.4 | Task 8: Platform ML Engine & Ensemble
PHASE 3.4 | Subtask 8.1: ThreadPool Parallel Trainer | Execute parallel candidate training across background threads using ThreadPoolExecutor. | High | Complete | 100 | aiconnex_agent/platform/platform_node.py | 2026-07-31 | 2026-07-31 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Max 3 parallel worker threads. Isolates model training jobs while tracking execution status.
PHASE 3.4 | Subtask 8.2: Stacked Ensemble Meta-Learner | Train meta-learner combining out-of-fold predictions from base candidate models. | High | Complete | 100 | aiconnex_ml/regression/ensemble.py | 2026-07-31 | 2026-07-31 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Uses real regression trainer. Produces stacked model combining strengths of candidate algorithms.
PHASE 3.4 | Task 9: MCDA Evaluation Triad
PHASE 3.4 | Subtask 9.1: Scorer Agent Evaluation | Calculate hard quantitative metrics (R2, MAE, RMSE, MAPE, Latency, Size). | High | Complete | 100 | aiconnex_agent/platform/evaluation/scorer_agent.py | 2026-07-31 | 2026-07-31 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | 50% weight in MCDA score. Computes rigorous statistical scorecards across all candidate runs.
PHASE 3.4 | Subtask 9.2: LLM Judge Agent Evaluation | Evaluate model compliance against physical domain constraints using LLM rubric. | High | Complete | 100 | aiconnex_agent/platform/evaluation/judge_agent.py | 2026-07-31 | 2026-07-31 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | 30% weight in MCDA score. Verifies physical process boundaries and domain constraint safety.
PHASE 3.4 | Subtask 9.3: Selector Agent Winner Pick | Compute final MCDA scores (50% Scorer + 30% Judge + 20% Intent) and select winner. | High | Complete | 100 | aiconnex_agent/platform/evaluation/selector_agent.py | 2026-07-31 | 2026-07-31 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Fair multi-criteria decision. Selects champion model and generates clear selection summary.
PHASE 3.5 | Task 10: Telemetry & MLflow
PHASE 3.5 | Subtask 10.1: Multi-Node Emitters | Emit telemetry events for Parser, Planner, Scout, HITL, and Platform nodes. | High | Complete | 100 | telemetry/emitters.py | 2026-07-31 | 2026-07-31 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Covers all 5 pipeline phases. Provides real-time event streaming for UI and CLI progress.
PHASE 3.5 | Subtask 10.2: MLflow SQLite Store Setup | Store experiment runs, metrics, parameters, and artifacts in ./mlruns. | Medium | Complete | 100 | ./mlruns SQLite Store | 2026-07-31 | 2026-07-31 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Complete experiment history. Accessible via local MLflow dashboard for model auditing.
PHASE 3.5 | Task 11: CLI Orchestrator & Manifests
PHASE 3.5 | Subtask 11.1: End-to-End Terminal Runner | Wire interactive terminal pipeline orchestrator running Phase 1 to Phase 5. | High | Complete | 100 | terminal_runner.py | 2026-07-31 | 2026-07-31 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Fully tested in terminal. Provides complete CLI user experience without web server dependency.
PHASE 3.5 | Subtask 11.2: 3-Layer Manifest Builder | Package Conversation, Discovery, and Decision manifests into compilation_package.json. | High | Complete | 100 | aiconnex_agent/platform/manifest_builder.py | 2026-07-31 | 2026-07-31 | None | https://github.com/AJ6002/aiconnex_demo/tree/30jul | Immutable handoff package. Bundles all session artifacts into standardized handoff folder.
PHASE 3.6 | Task 12: UI Branch Sync & Integration
PHASE 3.6 | Subtask 12.1: Merge 30jul into new-chat-UI | Merge all Phase 3 agentic backend commits from 30jul branch into new-chat-UI. | High | In Progress | 50 | Git Merge Commit | 2026-08-03 |  | Waiting for branch switch (Checkout new-chat-UI branch) | https://github.com/AJ6002/aiconnex_demo/tree/new-chat-UI | Branch sync in progress. Ensures new UI shell contains latest LangGraph orchestrator.
PHASE 3.6 | Subtask 12.2: Connect Flask API to React UI | Connect React frontend chat components to the live agentic backend API endpoints. | High | Pending | 0 | React UI + Flask API | 2026-08-03 |  | Depends on Subtask 12.1 (Awaiting branch merge completion) | https://github.com/AJ6002/aiconnex_demo/tree/new-chat-UI | Web UI connection milestone. Enables real-time streaming of agent thought logs to chat.
PHASE 3.6 | Subtask 12.3: Terminal E2E Verification & Test Validation | Run full regression test suite and terminal runner verification on merged branch. | High | Pending | 0 | tests/test_terminal_e2e.py | 2026-08-03 |  | Depends on Subtask 12.2 (Awaiting UI API endpoint readiness) | https://github.com/AJ6002/aiconnex_demo/tree/new-chat-UI | End-to-end validation. Ensures 100% green test suite status before staging release.
PHASE 3.7 | Task 13: Merge UI + Backend - v1
PHASE 3.7 | Subtask 13.1: Initial UI & Backend v1 Shell Merge | Initial merge of the frontend UI shell with the backend v1 codebase. | High | In Progress | 50 | frontend/ + aiconnex_agent/ | 2026-08-03 | 2026-08-03 | Awaiting UI shell code (Frontend React repository sync) | https://github.com/AJ6002/aiconnex_demo/tree/new-chat-UI | Initial UI shell merge. Combines basic React chat layout with backend agent entrypoints.
PHASE 3.8 | Task 14: Dataset → Terminal
PHASE 3.8 | Subtask 14.1: Direct Terminal Dataset Ingestion | Passing raw datasets directly into the terminal runner for Phase 1 compilation. | High | In Progress | 40 | terminal_runner.py | 2026-08-03 | 2026-08-04 | None (Actively in development) | https://github.com/AJ6002/aiconnex_demo/tree/new-chat-UI | Terminal dataset ingestion. Allows instant CLI ingestion of raw CSV/ZIP files without Web UI.
PHASE 3.9 | Task 15: In-Training Pipeline
PHASE 3.9 | Subtask 15.1: Live Training & Telemetry Pipeline | Executing parallel candidate model training, stacked ensembling, and real-time monitoring. | High | Pending | 20 | platform_node.py + telemetry/ | 2026-08-04 | 2026-08-04 | Depends on Task 14 (CLI dataset compiler completion) | https://github.com/AJ6002/aiconnex_demo/tree/new-chat-UI | Training execution & progress monitoring. Streams live training progress and epoch metrics.
PHASE 3.10 | Task 16: UI Backend Integration v2
PHASE 3.10 | Subtask 16.1: Bi-Directional React UI & Flask Sync | Full two-way integration connecting the React frontend UI to live backend Flask/Agent endpoints. | Critical | Pending | 0 | React UI + Flask API | 2026-08-04 | 2026-08-05 | Depends on Task 13 (v1 shell merge completion) | https://github.com/AJ6002/aiconnex_demo/tree/new-chat-UI | Complete integration v2. Enables seamless two-way HITL interaction and model download.
PHASE 3.11 | Task 17: CRUD & Testing + Cost Estimation
PHASE 3.11 | Subtask 17.1: Data CRUD, Test Suite & LLM Cost Engine | Implementing data CRUD operations, test suite execution, and LLM token/compute cost estimation. | High | Pending | 0 | chatbot/backend/ + tests/ | 2026-08-05 | 2026-08-05 | Depends on Task 16 (Full API sync completion) | https://github.com/AJ6002/aiconnex_demo/tree/new-chat-UI | CRUD, testing, & cost estimation. Calculates estimated LLM token usage and execution cost.
PHASE 3.12 | Task 18: D.S. Testing for Multiple Industries
PHASE 3.12 | Subtask 18.1: Multi-Industry Data Science Validation | Data Science validation and domain testing across multiple industrial datasets (ETP effluent, aircraft sensors, manufacturing, etc.). | High | Pending | 0 | tests/benchmarks/ | 2026-08-05 | 2026-08-05 | Depends on Task 17 (Test runner & benchmark setup) | https://github.com/AJ6002/aiconnex_demo/tree/new-chat-UI | Multi-industry DS domain validation. Validates model accuracy and robustness across 3+ industry datasets.