## Sheet1
Task_ID | Timeline_Phase | Category | Task_Description | Status | Type | Start_Date | End_Date | Notes_Context | Start_Offset_Days | Duration_Days
T001 | Yesterday | Preprocessing & Evaluation | Verified data preprocessing and model evaluation workflow. | Completed | Completed Task | 2026-07-16 | 2026-07-16 | Baseline data prep and model validation verified. | 0 | 1
T002 | Yesterday | SageMaker Pipeline | Explored SageMaker training instance requirements and pipeline feasibility. | Completed | Completed Task | 2026-07-16 | 2026-07-16 | Identified instance needs for production pipeline. | 0 | 1
T003 | Yesterday | AWS Quota | SageMaker training jobs blocked due to 0 quota for ml.m5.large. | Blocked | Blocked Task | 2026-07-16 | 2026-07-17 | Quota is 0. Prevents running any training jobs. | 0 | 1
T004 | Yesterday | AWS Administration | Created a new AWS account. | Completed | Action Taken | 2026-07-16 | 2026-07-16 | Fresh AWS account to isolate development. | 0 | 1
T005 | Yesterday | AWS Quota | Submitted SageMaker service quota increase requests. | Completed | Action Taken | 2026-07-16 | 2026-07-16 | Submitted request; awaiting AWS approval for ml.m5.large. | 0 | 1
T006 | Yesterday | AWS Administration | Verified AWS access. | Completed | Action Taken | 2026-07-16 | 2026-07-16 | Checked credentials; verified CLI/SDK access. | 0 | 1
T007 | Yesterday | AWS IAM | Created the required IAM execution role. | Completed | Action Taken | 2026-07-16 | 2026-07-16 | Configured with necessary S3, SageMaker, & CloudWatch permissions. | 0 | 1
T008 | Today | Airflow Integration | Verified that SageMaker SDK pipelines can be imported into Apache Airflow (Unified Studio) as a visual DAG. | Completed | Completed Task | 2026-07-17 | 2026-07-17 | Successfully verified the visual DAG import mechanism. | 1 | 1
T009 | Today | Pipeline Design | Completed the design of the 12-node production ML pipeline (Data Cleaning → Model Registry). | Completed | Completed Task | 2026-07-17 | 2026-07-17 | Layout and connections of all 12 stages finalized. | 1 | 1
T010 | Today | Pipeline Design | Designed a dynamic manifest.json metadata contract to support multiple algorithms (Regression / Anomaly Detection) using a single pipeline. | Completed | Completed Task | 2026-07-17 | 2026-07-17 | Contract allows single-pipeline multi-algorithm support. | 1 | 1
T011 | Today | Sorba AI Integration | Reviewed the Sorba AI Trainer Toolkit architecture and capabilities for potential integration. | Completed | Completed Task | 2026-07-17 | 2026-07-17 | Evaluated architecture for compatibility. | 1 | 1
T012 | Today | Script Development | Begin developing modular Python scripts for: Data Cleaning, Data Validation, Data Splitting. | In Progress | In Progress | 2026-07-17 | 2026-07-18 | Scripts currently being written and tested locally. | 1 | 1
T013 | Today | SageMaker Pipeline | Package modular Python scripts as SageMaker Processing Jobs. | In Progress | In Progress | 2026-07-17 | 2026-07-18 | Packaging scripts into containerized processing steps. | 1 | 1
T014 | Tomorrow / Next Steps | SageMaker Pipeline | Implement the complete SageMaker SDK pipeline by connecting all 12 pipeline stages. | Planned | Planned Task | 2026-07-18 | 2026-07-19 | Connecting all stages end-to-end. | 2 | 1
T015 | Tomorrow / Next Steps | Pipeline Validation | Execute end-to-end pipeline validation using the C-MAPSS dataset (Regression XGBoost & Anomaly Detection Isolation Forest). | Planned | Planned Task | 2026-07-19 | 2026-07-20 | Validation with target datasets. | 3 | 1
T016 | Tomorrow / Next Steps | Pipeline Validation | Test external pipeline execution through the AWS CLI with runtime parameters. | Planned | Planned Task | 2026-07-20 | 2026-07-20 | Command line validation. | 4 | 1
T017 | Tomorrow / Next Steps | Agentic Monitoring | Design an Agentic Monitoring architecture (e.g., Bedrock Agents) for model drift detection, automated retraining, and future pipeline optimization. | Planned | Planned Task | 2026-07-20 | 2026-07-22 | Future architectural work for continuous operations. | 4 | 2