## Sheet1
Task_ID | Timeline_Phase | Category | Task_Description | Status | Start_Date | End_Date | Start_Offset_Days | Duration_Days
T001 | Yesterday | Preprocessing & Evaluation | Verified data preprocessing and model evaluation workflow. | Completed | 2026-07-16 | 2026-07-16 | 0 | 1
T002 | Yesterday | SageMaker Pipeline | Explored SageMaker training instance requirements and pipeline feasibility. | Completed | 2026-07-16 | 2026-07-16 | 0 | 1
T003 | Yesterday | AWS Quota | SageMaker training jobs blocked due to 0 quota for ml.m5.large. | Blocked | 2026-07-16 | 2026-07-17 | 0 | 1
T004 | Yesterday | AWS Administration | Created a new AWS account. | Completed | 2026-07-16 | 2026-07-16 | 0 | 1
T005 | Yesterday | AWS Quota | Submitted SageMaker service quota increase requests. | Completed | 2026-07-16 | 2026-07-16 | 0 | 1
T006 | Yesterday | AWS Administration | Verified AWS access. | Completed | 2026-07-16 | 2026-07-16 | 0 | 1
T007 | Yesterday | AWS IAM | Created the required IAM execution role. | Completed | 2026-07-16 | 2026-07-16 | 0 | 1
T008 | Today | Airflow Integration | Verified SageMaker SDK pipelines DAG import in Airflow. | Completed | 2026-07-17 | 2026-07-17 | 1 | 1
T009 | Today | Pipeline Design | Completed design of 12-node production ML pipeline. | Completed | 2026-07-17 | 2026-07-17 | 1 | 1
T010 | Today | Pipeline Design | Designed dynamic manifest.json metadata contract. | Completed | 2026-07-17 | 2026-07-17 | 1 | 1
T011 | Today | Sorba AI Integration | Reviewed Sorba AI Trainer Toolkit architecture. | Completed | 2026-07-17 | 2026-07-17 | 1 | 1
T012 | Today | Script Development | Develop modular Python scripts (Cleaning, Validation, Splitting). | In Progress | 2026-07-17 | 2026-07-18 | 1 | 1
T013 | Today | SageMaker Pipeline | Package modular scripts as SageMaker Processing Jobs. | In Progress | 2026-07-17 | 2026-07-18 | 1 | 1
T014 | Tomorrow / Next Steps | SageMaker Pipeline | Implement complete 12-stage SageMaker SDK pipeline. | Planned | 2026-07-18 | 2026-07-19 | 2 | 1
T015 | Tomorrow / Next Steps | Pipeline Validation | Execute end-to-end pipeline validation using C-MAPSS dataset. | Planned | 2026-07-19 | 2026-07-20 | 3 | 1
T016 | Tomorrow / Next Steps | Pipeline Validation | Test external pipeline execution through AWS CLI. | Planned | 2026-07-20 | 2026-07-20 | 4 | 1
T017 | Tomorrow / Next Steps | Agentic Monitoring | Design Agentic Monitoring architecture (Bedrock Agents). | Planned | 2026-07-20 | 2026-07-22 | 4 | 2